A Step-By-Step Process for Developing

Annual Goals, Strategies, and Action Plans

Each area of ministry should annually set SMARTER (specific, measurable, attainable, relevant, timed, evaluate, revise) ministry goals and involve in service opportunities as many members as possible.  Consider selecting coordinators and forming ministry teams to assist.  Provide position descriptions and training/mentoring for all.

Utilize whichever steps and tools are helpful in accomplishing your ministry goals.

STEP ONE: Identify and prioritize your annual ministry goals.

Brainstorm and consider the member input provided during the listening sessions.

Apply the following criteria to prioritize your ministry goals.

- Which tasks (if accomplished) would have the greatest or broadest spiritual impact?

- Which tasks most closely support the church’s mission of outreach and nurture?

- Which tasks must be sequenced first (because other goals depend on their accomplishment)?

- Which tasks make the best use of available gifts and talents in your congregation?

List your top three goals in priority order:

1. (Type: _O_) _To provide witness training for our members by developing a 4 or 6-week “Sharing our Savior” interactive Bible study, with participants sharing weekly witness opportunities_______________________________________________________

2. (Type: _C_) _To discover additional ways of growing our prospect list and involve trained members in nurturing our prospects by making caring contacts during the year______________________________________________________________________

3. (Type: _R_) _To build bridges to our neighbors through acts of service so that we earn the right to tell them about Jesus and create a more positive reputation for our congregation_______________________________________________________________

Eventually you’ll design strategies/action plans for other goals within your ministry area.

STEP TWO: With each of the above prioritized ministry goals, determine its type.

O = One-Time Effort (e.g. outreach seminar in community) requires only an action plan

R = Recurring Process (e.g. budgeting) requires a procedure document and/or flow chart

C = Complex “Game Plan” (e.g. summer camp) requires a strategy of sequential steps

STEP THREE: Identify the issues – positive and negative – that may impact the effort to achieve this goal.

(Consider using the “Identify Issues & Brainstorm Options” sheet.)

Positive: Consider people, strengths, resources, healthy attitudes, structures, etc.

Negative: Consider obstacles, problems, weaknesses, poor attitudes, etc.

STEP FOUR: Brainstorm options that can address the issues and achieve the goal.

(Continue using the “Identify Issues & Brainstorm Options” sheet.)

Some goals may not face significant issues or allow for multiple options.

1. Talk about different ways the goal could be achieved:

- Utilizing positive issues

- Resolving negative issues

2. Record brief, broad descriptions of any feasible options.

STEP FIVE: Agree on the best option (strategy) and break it down into as many significant, sequential steps as necessary.

(Consider using the “Strategy of Sequential Steps”

or “Flow Chart” sheet, whichever works best.)

STEP SIX: Design an “action plan” – who will do what by when – for each step of the strategy (if needed) or for goals that require only an action plan.

(Consider using the “Action Plans” or “Flow Chart” sheet, whichever works best.)

STEP SEVEN: Develop a procedure document (step-by-step instructions, possibly with dates) and/or flow chart for every recurring process.

More sample sheets…

(

# Identify Issues & Brainstorm Options   [Steps 3 & 4]

Coordinator: ___Jane T.______________________________ Date: _January 10, 20XX__

Other Ministry Partners: __Bill O., Kathy Z., Tom P._______________________________

__________________________________________________________________________

Ministry Goal: __To develop a summer camp for children for community outreach and the spiritual nurture of children________________________________________

( Identify issues (positive and negative) that may impact the effort to achieve this goal.

Positive (people/strengths/resources)               Negative (obstacles/problems/weaknesses)

_Members with teaching background____    _We’ve never done this before__________

_Capable musicians in our congregation_    _Don’t have athletic field or gym_________

_Lots of kids in the community_________    _Maybe not enough members to help_____

_Parents would welcome this__________    _No perfect time to schedule/vacations___

_Some of our teens could assist________    _Hard to estimate costs (1st time)________

(  Brainstorm options that can address the issues and achieve this goal.

- _“Bible Basketball Camp,” one week, rent gym in town, use our high school basketball players, pastor does 30-minute Bible study daily (focus on Jesus), for boys and girls grades 4-6, strive to build relationships__________________________

- _“Christian Music Camp,” one week or one day/night for several weeks, in a worship setting with lessons from Psalms, teach children about God’s gift of music (beginner and intermediate) with keyboards (other instruments?)________________

- _“Summer Reading Camp” or “Summer Math Camp” for one/two weeks, remedial tutoring one-on-one, devotions built around what God did to make us special to him, Bible story books used and then given to the kids____________________________

## Agree on the best option.  #2 & 3 (adapted, combined)

Copies: ( _Outreach Board____    ( _Pastor____________    ( _Youth Nurture Board_

# Strategy of Sequential Steps   [Step 5]

Coordinator: _Jane T.________________________________ Date: _January 21, 20XX_

Other Ministry Partners: ___ Bill O., Kathy Z., Tom P._____________________________

__________________________________________________________________________

Ministry Goal: _To develop a “Christian Development Camp” for children (grades 1-4), three 4-day weeks, one each on music, reading, and math___________________

( When you have completed the steps, add month and/or year to each step.

## Month/Year       Strategic Steps

_Sept. ‘XX_	1. _Develop curriculum and activities, both Bible lessons and academic skills-related, input from educators and WELS Youth and Family Ministry___________

_Oct. ‘XX__	2. _Recruit teachers, aids, and a coordinator for each week.  Crete roles that “fit well” for as many members as possible_________________________________

_Feb. ‘XX__	3. _Draw up daily/weekly schedules, determine space needs, materials, and snacks.  Initial announcements in congregation and community._______________

_Mar. ‘XX__	4. _Develop a promotion and recruitment campaign, utilizing free publicity, contacts in public schools, and our prospect list________________________

_Apr. ‘XX__	5. _Design an evangelism strategy to meet and follow up on families, assign responsibilities for each role in the strategy______________________________

_June ‘XX_	6. _Host the three events as planned, check in with coordinator daily, celebrate, troubleshoot, pray_________________________________________________

_Aug. ‘XX__	7. _Evaluate strategy, process, events, outreach potential, make decisions on having another “camp”___________________________________________________

Copies: ( _Outreach Board____    ( _Pastor____________    ( _Youth Nurture Board_

Flow Chart   [Steps 5, 6, or 7]

Coordinator: ___David T._____________________________ Date: _Oct. 21, 20XX______

Other Ministry Partners: _Gail G., Bobby D., Lois K., Pastor_______________________

________________________________________________________________________

Ministry Goal: _To help each new member understand volunteer ministry, discover his/her gifts, and find appropriate opportunities to serve______________________

Instructions:

- At the top of each “Who” column identify a person with some responsibility in the process.

- Note dates in the “Checkpoint” (Time Frame) column.

- Next to each “Checkpoint” list the task the person is responsible for doing.

| Checkpoint (Time Frame) | Who: _Pastor____ | Who: __Member_ Min. Coord. | Who: Interviewers | Who: _Director of Min. Areas_ | Who: ___New___ _Members_ |
| --- | --- | --- | --- | --- | --- |
| Feb. 1, May 1, Aug. 1, Nov. 1 2 weeks prior to each quarterly session Quarterly Sessions Within: 1 week 3 weeks 5 weeks | Provides info on new members | Receives info Invites new members to Sat. sessions each quarter Schedules interviews with each new member Arranges training Contact directors with info Follow up with directors | Are trained | Receives info Contacts new members | Are invited Attend sessions Contacted |

Copies: ( _Dir. of Min. Areas__    ( _Pastor_____________    ( _Interviewers_______

## Action Plans   [Step 6]

Coordinator: ____Jim B.______________________________ Date: _June 10, 20XX_____

Other Ministry Partners: __Susan S., Ken K., John D., Kim O., Liz W., Steve A.________

__________________________________________________________________________

Ministry Goal: _To develop a January “Marriage Enrichment Retreat” in a comfortable and sensibly priced setting, use outside “expert” to lead the sessions

Strategy Step: ___________________________________________________________

# Desired Completion Date of this ministry goal or strategy step: __January 15, 20XX___

WHO?                  DOES WHAT?                                                                            BY WHEN?

_Susan____  (  _Secures a January weekend for up to 20 couples___  (  _Aug. 1____

_(max. 75 miles, $175 per couple)________________

_Ken______  (  _Contacts WELS/WLCFS to secure expert retreat ____  (  _Sept. 15__

_leader and maintains contact___________________

_Liz_______  (  _Creates a publicity plan, in phases, including______  (  Oct 30-Dec 1

_personal invitations to all couples in congregation_

_John_____  (  _Works with pastor, develops devotions and an____  (  _Nov. 15___

_informal worship experience___________________

_Kim______  (  _Develops a schedule that includes activity options__  (  _Nov 15___

_for couples that add “romance” (_______________

_Steve/Jim_  (  _Arrange for the copying of materials, availability of_  (  _Dec. 15-30

_snacks, coordination of transportation____________

_All of us___  (  _Evaluate the January 10-12 retreat and identify_____  (  _Jan. 30__

_blessings and concerns________________________

(You may find it helpful to “work backwards” from the desired completion date.)

Copies: ( _Family Nurture Bd._    ( _Pastor_____________    ( ___________________

Sample Procedure Document

Volunteer Communion Preparation

(The communion ware, wafers, and wine are located in the kitchen under the microwave.)

On the day of communion, prior to worship, or on the day before communion:

- Fill the wafer container and place it on the shelf in the chancel.  (See diagram.)

- Fill the 40 plastic communion cups in the communion trays (Summer:  Seven trays;  School Year:  Eight trays).  Check for an open wine bottle in the refrigerator and use that wine first.  Please, fill the wine cups just half full, at the level of the tray.  (The cups are difficult for some people to handle if they are too full.)  Refrigeration of filled wine trays is not recommended.

- Set the small wooden table from the sacristy in front of the church and put the tray for the deposit of used wine cups on the table.  (See diagram.)  The tray is located in the kitchen near the communion supplies.

- Put the base for the wine trays and a folded white cloth on the altar.  (See diagram.)

- Early Sunday service:  Place four (Summer) or five (School year) filled wine trays on the shelf in the chancel, next to the wafer container.  The other trays can be placed on the desk in the sacristy and are covered with a white cloth.  Late Sunday service:  Place three (Summer) or four (School year) filled wine trays on the chancel shelf.  [Summer Monday service:  Two trays;  School year Saturday service:  Three trays]  The trays in the chancel are then covered with a colored cloth which matches the color of the seasonal paraments.  (The cloths are located in the wall cabinet at the entrance of the sacristy.)

Note:  Please remember to set up the communion ware for Sunday (after a Saturday evening service), for Monday (after the late Sunday service), and for the late service (following the early service).  Also, please empty and wash the tray used for the deposit of empty wine glasses after each communion service.  (Discard the used communion cups.)

Clean up after communion services:

- Thoroughly clean all items used for setting up communion and put everything back in its place.  (Use warm water to clean wine/finger prints from communion ware.  A clean white cloth, 100% cotton dish towel, is to be used to wipe communion ware dry.)  Please handle communion ware carefully.

- Contact the church office (call XXX-XXXX or leave a dated, signed note) when wine, wafers, or plastic communion cups begin to run low.  More will be ordered.

- Contact our communion coordinator, Judy Jones (XXX-XXXX), if you have questions.

Thank you for your service to your Lord and his people!

Planning Grids

Church Council &

Boards (or individuals in some congregations)…

- Give high priority to completing your planning grids.  They keep you, as leaders, focused on your goals.  Board grids (area of ministry grids) are created first.  These are then combined to create the council grid.

- It’s helpful to display (perhaps 3 ft. X 5 ft.) your Ministry Plan in a prominent location.  This works great for reminding all members where you’re headed, sharing your plan with prospects, and helping volunteers to see the many opportunities for service in their church.

These grids need to be updated annually, shortly after the review of your Ministry Plan.  This ensures that your ministry goals and subsequent strategies and action plans remain relevant.

Multi-Year Planning Grid – Board (or individual): ___Elders (Director)____

| Ministry Goals | 20__ 1st Yr. | 20__ 2nd Yr. | 20__ 3rd Yr. | 20__ 4th Yr. | 20__ 5th Yr. | 20__ 6th Yr. |
| --- | --- | --- | --- | --- | --- | --- |
| Musician Database | Identify Persons with Skills Interview Each Provide List to Music Coordinator | Identify New Members with Skills - Ongoing Update List Annually |  |  |  |  |
| Provide Usher & Greeter Training | Review/Revise Position Descrip. Invite All Current & Interested Provide Two Training Sessions |  | Review/Revise Position Descrip. Invite All Current & Interested Provide Two Training Sessions |  | Review/Revise Position Descrip. Invite All Current & Interested Provide Two Training Sessions |  |
| Provide Course on Worship | Discuss Dates & Material Options with Pastor | Assist with Promotion Pastor Teaches Course |  | Assist with Promotion Pastor Teaches Course |  | Assess Needs for Additional Study |
| Implement Lay Readers | Prepare Members to Understand Discuss Schedule & Guidelines | Enlist Participants Train Participants Schedule Readers & Implement | Review & Expand Lay Reader Prog. | Annual Review | Annual Review | Annual Review |
| Trail Sermon Prep Group | Establish Plan | Appoint (Both Genders) Participants Initiate Plan | Annual Review | Annual Review | Annual Review | Annual Review |
| Staffed Nursery |  | Contact Other Congregations Prepare PD Enlist Coordinator | Write Guidelines for Nursery Use Implement Staffed Nursery | Annual Review | Annual Review | Annual Review |
| Review H. C. Distribution |  |  |  | Establish Plan Review History Seek Member Input | Experiment with Viable Options Seek Member Input | Review/Revise? |
| Etc. | Etc. | Etc. | Etc. | Etc. | Etc. | Etc. |

Annual Ministry Grid – Board (or individual): ___Elders (Director)___  Year:_20XX_

| Goals | Jan. | Feb. | Mar. | Apr. | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Worship | Input from Pastor on Worship Concerns & Oppor. |  | Usher & Greeter Training (Usher Coord.) | Input from Pastor on Worship Concerns & Oppor. | Newsletter Article from Elders (by ____) | Bulletin Insert by Elders (by ____) | Input from Pastor on Worship Concerns & Oppor. | Musician Database (Music Coord.) Updated Annually | Set Plan to Use Lay Readers | Input from Pastor on Worship Concerns & Oppor. | Prepare Schedule & Guidelines for Lay Readers | Discuss Dates & Options for Worship Course |
| Strayed & Straying | Discuss Early Warning System | Share Info with Cong. | Implement Early Warning System | Continue to Share Info with Cong. | Begin to Assign Contacts with Staying | Continue Contacts & Written Reports | Continue Contacts | Continue Contacts | Consider Using Assistants & Provide Training | Continue Contacts | Review Process | Continue Contacts |
| Elder Growth & Devotions | Devotion by Pastor & Develop Personal Growth Plan | Devotion by Elder (______) | Devotion by Elder (______) | Devotion by Elder (______) | Devotion by Elder (______) | Devotion by Pastor & Discuss Personal Growth Plan | Devotion by Elder (______) | Devotion by Elder (______) | Devotion by Elder (______) | Devotion by Elder (______) | Devotion by Pastor & Update Personal Growth Plan | Devotion by Elder (______) |
| Etc. |  |  |  |  |  |  |  |  |  |  |  |  |

Notes: ____________________________________________________________________________________________________
_________________________________________________________________________________________________________

Multi-Year Planning Grid – _______ Lutheran Church Council

| Ministry Areas | 20__ 1st Yr. | 20__ 2nd Yr. | 20__ 3rd Yr. | 20__ 4th Yr. | 20__ 5th Yr. | 20__ 6th Yr. |
| --- | --- | --- | --- | --- | --- | --- |
| Worship | Provide Welcome Packets to Visitors Create Musician Database Provide Greeter & Usher Training | Pastor Teaches Worship Course Implement Lay Readers Pilot Sermon Prep Group | Provide Facility Task Force Input Weekly Children’s Messages Provide Staffed Nursery | Review Facility T. F. Proposals Pilot Saturday PM Worship Study Communion Distribution | Study Facility Use Options Discuss Alternative Worship Options Trial Use of PP During Worship | Begin Using New Facility Staff Visitor Welcome Center Pilot Alternative Worship |
| Adult Nurture | Begin Classes in Core Curriculum Begin Email Devotion Program Add Bible Class & EMV Recruitment | Offer More Classes Core Curriculum Train 2 Lay Bible Study Facilitators Stew. (Whole Life) Bible Study | Repeat/Continue Core Curriculum 2nd Phase Bible Study Recruit. Plan/Conduct 1st Marriage Retreat | Review Classes in Core Curriculum Train 2 Lay Bible Study Facilitators Stew. Cottage Meetings | Repeat/Continue Core Curriculum Pilot Small Group Bible Studies EMV Bible Study Recruitment | Repeat/Continue Core Curriculum Train 2 Lay Bible Study Facilitators Quarterly Saturday Stew. Seminars |
| Outreach | Add New Resident Program Sharing Our Savior Bible Study Expand Prospect Newsletter | Train 2 Additional Evangelists Plan/Conduct 1st Outreach Seminar Begin Quarterly Direct Mailings | Position Public Relations Person Plan/Conduct 2nd Outreach Seminar Implement Care Center Program | Train 2 Additional Evangelists Plan/Conduct 3rd Outreach Seminar Organize Program for Transportation | Begin Community Events (2/year) Sharing Our Savior Bible Study Assimilation Plan Review | Train 2 Additional Evangelists Plan Community Events (2/year) 1st Community Impact Effort |
| Member Ministry | Etc. | Etc. | Etc. | Etc. | Etc. | Etc. |
| Etc. |  |  |  |  |  |  |
| Etc. |  |  |  |  |  |  |
| Etc. |  |  |  |  |  |  |

Notes: ____________________________________________________________________________________________________
_________________________________________________________________________________________________________

# Text boxes

Sample

Sheets

Sample

Sheets

1. Pastor’s study on gifts, 2. Coordinator’s Spiritual Gifts and Personality Profiles, 3. Interviews determine how gifts, interests, personality, and schedule best match roles (use PDs)